## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass | AV 10/22 | Pass | JRG, 11/7
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass | AV 10/22 | Pass | JRG, 11/7
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | Pass | AV 10/22 | Pass | JRG, Based on setup the needs page will never be empty
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass | AV 10/22 | Pass | JRG, 11/7
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass | AV 10/22 | Pass | JRG, 11/7
As a helper I want to be able to log into the Ufund service and see my previous needs in my cart, and look for new needs in the cupboard | GIVEN I login successfully with a regular user account, I should be able to ACCESS the rest of system, including needs from the basket and cupboard | Pass | AV 10/22 | Pass | JRG, 11/7
| GIVEN I login successfully with an admin account, THEN I should be able to add, remove, and edit the data of all needs, BUT not be able to access the contents of user's need baskets | Pass | AV 10/22 | Pass | JRG, 11/7
| GIVEN I use an invalid username to login, THEN I should receive an error and be prevented from accessing the system | Pass | AV 10/22 | Pass | JRG, 11/7
AS a helper i want to be able to logout of the service and store the needs in my basket for a following login | GIVEN I logout of my account, the system should save whatever needs are in my cart for following logins. | Pass | AV 10/22 | Pass | JRG, 11/7
As a helper I WANT to able to Remove an item from my cart if I do not want to buy that item any more. | GIVEN I click on my basket I can view my current needs | Pass | AV 10/22 | Pass | JRG, 11/7
| GIVEN I click the remove button on one of my needs currently in the basket, it should leave the basket. | Pass | AV 10/22 | Pass | JRG, 11/7
AS a helper I WANT to select an need from the cupboard and add it to the basket to be bought | Given I click on an add button next to a specific need, that need should be put in my basket for purchase | Pass | AV 10/22 | Pass | JRG, 11/7
AS a Developer I WANT to submit a request to create a new need (name [unique], cost, quantity, type) SO THAT it is added to the cupboard. | GIVEN I click on the add button, I can create a new need for the cupboard | Pass | AV 10/22 | Pass | JRG, 11/7
| GIVEN I click on the edit button on a specific need, I can edit the existing variables of said need. | Pass | AV 10/22 | Pass | JRG, 11/7
| GIVEN I click on the delete button on a specific need, I can remove that need from the cupboard | Pass | AV 10/22 | Pass | JRG, 11/7
AS a helper I WANT to search for a need SO THAT I can add it to my basket | GIVEN that I search for a need the system searches the cupboard and returns needs that has the searched string in it's name. |  |  | Pass | JRG, 11/7
AS a USER, I WANT to view Leaderboard TO compare my total donation amount to other users. | GIVEN I checkout and spend money, THEN I should have my amount spent increased |  |  | Pass | JRG, 11/7
| GIVEN I checkout, spend money, spent more than the person in front of me, THEN my place on the leaderboard increases |  |  | Pass | JRG, 11/7
AS a USER I WANT to buy the needs in my basket TO help support the people affected by natural disasters. | GIVEN I have needs in my basket when I checkout THEN I should have needs in my basket to be bought. |  |  |  | Not implemented, yet
| GIVEN I do not have need in my basket THEN I should not be able to checkout with no needs. |  |  | Pass | JRG, The money amount should go back to zero
| GIVEN a user buys needs in their basket THEN the quantity of the need in the cupboard should decrease by that same amount. |  |  | Pass | JRG, 11/7
AS a user I WANT to filter the list of needs from available organizations to find what is best suited for my current situation. | GIVEN I filter for needs based on price, THEN I should receive a list of needs in order from Cheapest to Most Expensive and vice versa. |  |  |  | Not implemented, yet
| GIVEN I filter for needs alphabetically, THEN I should receive a list of needs in order from A to Z and vice versa. |  |  |  | Not implemented, yet
| GIVEN I filter for needs based on category, THEN I should receive a list of needs relating to said category. |  |  |  | Not implemented, yet
| GIVEN I filter for needs based on quantity, THEN I should receive a list of needs in order from that quantity from either more than or less than it. |  |  |  | Not implemented, yet